## Project Gantt Chart
PROJECT SCHEDULE & GANTT CHART
Task Name | Assigned To | Start Day | Duration | Progress (%) | W1 | W2 | W3 | W4
Keyword Research & Topic Silos | SEO Team | 1 | 5 | 100% | [■■■■■]
Hugo UI Kit & Layout Development | Dev Lead | 3 | 7 | 100% | [■■■ | ■■■■]
Cloudflare R2 Bucket & Worker Deploy | DevOps | 6 | 4 | 100% |  | [■■■■]
Content Production & Review | Editorial | 8 | 12 | 60% |  | [■■ | ■■■■■ | ■■■]